## Sheet1
PR-2022-007299 | SKYVIEW WEST - CENTRAL AVE. / AMANDA ST.
RESPONSE TO COMMENTS DATED 07/24/2024
Department | Comment | Response
Planning | Confirm if the landscaping clear utility areas. Such as easements or power poles around the perimeter and/or fronting central | Note included on plan LS-101 says "landscaping clears utility areas, easements and power poles"
Planning | For all lots and access areas, clarify all proposed uses and the development plan through each phase. If additional uses exist, each Use Specific Standard will need to be met and demonstrated as such. For example, Outdoor Vehicle Storage, Freight/Dispatch, & Transit facility. | The project involves the development of a 50,000 square foot concrete tilt-up building, including 3,000 square feet designated for office space. The facility is situated on a 13.25-acre site, with 9.03-acres dedicated to yard storage for larger equipment. The site and building will be leased to Stuart C. Irby Company, a privately owned national distributor of electrical equipment and parts. Irby is a key supplier for PNM, providing essential transformers and other equipment. The use of the facility will be the storage and distribution of electrical equipment for PNM. We have a current 10 year lease with Irby, and they have an option to expand the original 50,000 sf building to the east (phase 2), but the use will not change.
Planning | Provide additional elevation detail to demonstrate and explain compliance with all sections within 5-11-E. Specifically 5-11-E-2-b and 5-11-E-3. More detail is needed as the property is within the West Route 66 Activity Center. | Notes added to SDP-1 and SDP-3 stating compliance with IDO section 5-11-E. Street Facing Facades are defined in the IDO as being within 30’ of ROW. We have no facades in Phase 1 or Phase 2 that will be within 30’ of ROW on either Central or Amanda. The other note states that we have a 500 s.f. pedestrian gathering area and it is located with keyed note 17 on the site plan.
Planning | Confirm compliance with section 7 of the DPM Table 7.2.29 regarding Sidewalk width requirements, the landscape buffer, and Maintenance responsibilities. *After further discussion with Transportation Parks & Recreation, and the City Engineer, it was determined that a 10’ sidewalk would be needed. Trail would not be sufficient. *Clarify if dedication of right of way is needed for either trail or sidewalk. *Verification of standards per Transportation. Per previous sketch plat-- Along the frontage of Amanda St. a 5’ sidewalk is required in this area. Along the frontage of Central Ave. a 10’ sidewalk with curb & gutter is required as this is Principal Arterial within a Center. All sidewalks must have a 4-foot ADA pathway around all obstructions within right-of-way. ROW dedication may be required. All wok within the ROW shall be done under a work order and all infrastructure items placed on an infrastructure list. | 10’ sidewalk has been changed from asphalt to concrete along Central and dimensions have been added showing a 5’ wide sidewalk along Amanda. The dimensions show 10’ from curb to ROW which will leave an approximately 4’ buffer strip between sidewalk and Amanda street.
Planning | Clarify and confirm with engineering team that the Infrastructure List (IL) is ready to be finalized or if modifications are needed. | Infrastructure list was updated and completed 7.25.24 reflecting "10' Concrete Sidewalk" and note for pond stabilization
Planning | Once the IL is approved, a recorded Infrastructure Improvements Agreement to guarantee the infrastructure will need to be executed and recorded with the County Clerk prior to final sign off of the site plan. | Working with DRC to approve a financial guaranty amount and drafting IIA and LOC documents
Planning | Clarify the building height related to the standards of IDO section 5-9 Neighborhood edges. 30ft maximum within 100ftNR-C site is abutting R-T and R-A. | The 30 ft maximum height within 100ftNR-C site from ideo section 5-9 DOES NOT APPLY.The site plan has dimensions that clearly show the building being 120’ from the neighborhood edge. This is greater than the height restriction requirement within 100’ shown in IDO 5-9.
Planning | *Clarify dimensions of Edge buffer area. | Note included calling out "EDGE BUFFER Landscaping 14-16-5-6(e). Linear footage of buffer area noted as well. Per code 5-6e, 15' of edge buffer is required and you can see that there are four dimensions from the west side property line showing that we have more than 15' of the required landscape area for the edge buffer requirements. See sheet LS-101
Planning | Hydrology has an approved G&D. Transportation has approved the TCL. Clarify if Solid Waste and Fire & Rescue have approved the site plan. | Solid waste and fire and rescue BOTH have approved the site plan. Both sign offs were included in the submittal to the DFT
Planning | Provide a lighting plan with dimensions that meets IDO section 5-8. | Pole lighting is included in the site plan (SDP-1) along with note #2 in the general notes section saying "all site lighting shall comply with IDO section 14-16-5-8"
Planning | *Applicant must ensure that all revised and final Plan sheets are sealed and signed by a design professional licensed in the State of New Mexico. | All revised plan sheets were signed and sealed by licensed professionals in the state of NM
Planning | Provide landscaping including groundcover and some noninvasive shrubs in the following areas or provide clarification why it needs to be left blank: (central ROW) | See sheet LS-101. Landscaping including groundcover and non-invasive shrubs were added to the central ROW
Planning | Provide a tree planting detail to reflect this requirement. The organic mulch used under the trees can be counted towards non gravel mulch used on the site as discussed earlier under 5-6(C)(5)(c). Please make sure you are mention ‘Organic Mulch’ or arborist mulch on your planting details (not wood mulch). City of Albuquerque is not asking for wood mulch but Organic mulch (or Arborist mulch) per the IDO. Regardless, the note you have provided on the wood mulch has been sent to the City Forester and we will communicate his response with you. Thank you so much for bringing up your concern! | See revised note on sheet LS-103 on the tree planting detail that specifies organic mulch instead of wood mulch.
Planning | Per 5-6(C)(10)(d), if overhead distribution electric lines are present and large trees cannot be planted due to potential interferences with the electric lines, one ornamental tree with a mature height of 12 feet shall be planted per 20 feet of street frontage. New trees planted near electric transmission lines shall be no taller than 25 feet in height at maturity to avoid conflicts with existing electric facilities. Confirm compliance | Compliance is confirmed, see note that says "street trees are placed further back to avoid interfering with the utilities in the ROW" on sheet LS-101
Planning | Per 5-6(C)(10)(e), all screening and vegetation surrounding ground-mounted transformers and utility pads must allow 10 feet of clearance for access and to ensure the safety of the work crews and public during maintenance and repair. Confirm compliance with this code. Please confirm the location of transformer/s. | See added transformer location on sheet LS-101 with added note: "location of transformer with 10 feet of clearance for access"
Planning | Per 5-6(C)(10)(f), trees shall not be planted near existing or proposed street light poles. Confirm compliance with this code. | No trees will be planted near existing or proposed street light poles
Planning | Confirm whether or not any existing vegetation will be maintained. | No existing vegetation will be maintained
Planning | Where multi-family, mixed-use, or non-residential development other than industrial development occurs on a lot abutting or across an alley from a lot containing low-density residential development in an R-A, R-1, R-MC, R-T , or RML zone district, a buffer shall be provided along the lot line, as specified in Table 5-6-4 and for the relevant area below. 5-6(E)(2)(a) General A landscaped edge buffer area shall be provided on the subject property along the property line between the two properties. 1. If a wall at least 3 feet in height is provided or exists along the property line between the 2 properties, 1 tree at least 8 feet high at the time of planting shall be provided every for 15 feet along the wall, with spacing designed to minimize sound and light impacts of the proposed development on the adjacent property. 2. If no wall is provided or exists, 1 tree at least 6 feet tall at the time of planting and at least 25 feet tall at maturity and 3 shrubs shall be provided for every 25 feet along the lot line, with spacing designed to minimize sound, light, and noise impacts. Confirm compliance Where site is abutting properties within R-T zone to the west. Please see the image below for your reference: | Edge buffer requirements have been met. See notes and locations on landscaping plan that say "EDGE BUFFER LANDSCAPING 14-16-5-6(e) 1 tree and 3 shrubs per 25 linear feet for screening". See sheet LS-101
Planning | 5-6(F)(1)(i) Landscape buffers are required in the following locations, with minimum widths and design requirements as specified below. 1. Front Lot Edge General Any parking lot located within 30 feet of the front lot line shall be screened from the street either by a masonry wall constructed of a material similar in texture, appearance, and color to the street-facing façade of the primary building (but excluding exposed CMU block) at least 3 but not more than 4 feet in height, or by a landscape buffer at least 10 feet in width with a continuous line of evergreen Confirm compliance | Front edge buffering requirements have been met. See notes and locations on landscaping plan that say "Landscape Buffer parking lot screening. 20' wide, +3' high evergreen shrubbery". See sheet LS-101
Planning | Per 5-6(F)(2)(a) General, at least 10 percent of the parking lot area of lots containing 50 or fewer spaces, and at least 15 percent of the parking lot area of lots containing 50 or more spaces, shall be landscaped. Calculations must be added to the landscape plan data. | Calculation added to sheet LS-101. See "parking lot landscape area calculation"
Planning | One (1) tree is required per 10 parking spaces. Calculations must be added to the landscape plan data. | Calculation added to sheet LS-101. See "parking lot landscape area calculation"
Planning | No parking space may be more than 100 feet in any direction from a tree trunk. Calculations must be added to the landscape plan data. | See added 100' radii to sheet LS-101 which show there is no parking space more than 100 feet from the tree trunks in parking areas
Planning | At least 75 percent of the required parking area trees shall be deciduous canopy-type shade trees, capable of achieving a mature canopy diameter of at least 25 feet. Confirm compliance | Calculation added to sheet LS-101. See "parking lot landscape area calculation"
Planning | 5-6(G)(1)(b) In any R-ML, R-MH, Mixed-use, NR-C, NR-BP, NR-SU, or NR-PO zone district, roof-mounted mechanical equipment shall be screened by a parapet wall or similar feature that is an integral part of the building’s architectural design. The parapet wall or similar feature shall be sufficient to screen the mechanical equipment from all sides when viewed from 5 feet above ground level at any property line abutting a City park or trail, Major Public Open Space, major arroyo, or public street classified as a collector, arterial, or interstate highway. Confirm compliance with this code. | Compliance is confirmed. The parapet wall will be sufficient to screen mechanical equipment from all sides
Planning | Per 5-6(G)(2)(a), R-ML, R-MH, and Mixed-use Zone Districts, outdoor ground-mounted mechanical equipment shall be located where it is not visible from streets, City parks or trails, Major Public Open Space, or major arroyos adjacent to the lot or from adjacent properties to the maximum extent practicable. Confirm compliance with this code. | There will be no ground-mounted mechanical equipment. Compliance is confirmed
Planning | Where it is not practicable to locate ground-mounted mechanical equipment pursuant to Subsections (a) and (b) above, such equipment shall be screened from view by an opaque decorative wall or fence or a vegetative screen. 1. The wall or fence shall be of a height equal to or greater than the height of the mechanical equipment being screened and shall incorporate at least 1 of the primary materials and colors of the nearest wall of the primary building (but excluding exposed CMU block). 2. The vegetative screen shall be planted along the full length of the equipment to be screened and shall be of a height equal to or greater than the height of the equipment 11 to be screened at the time of planting. 3. No screening of ground-mounted solar energy equipment that would reduce the efficiency or effectiveness of the solar energy equipment is required. Confirm compliance with this code. | There will be no ground-mounted mechanical equipment. Compliance is confirmed
Planning | 5-6(G)(3) Loading, Service, and Refuse Areas Per 5-6(G)(3)(a) Covering Waste Containers, all waste containers and dumpsters shall be in a roofed enclosure or be equipped with and use a lid covering and shall be designed so that stormwater runoff does not reach storm drain inlets. Confirm compliance with this code | We added a note to SDP-1 near the trash enclosure that states that the dumpster will have a lid covering.
Planning | Where it is not practicable to locate the loading, service, and refuse areas pursuant to Subsections (c) and (d) above, they shall be screened from view by an opaque decorative wall or fence at least 6 feet tall but not more than 8 feet tall that incorporates at least 1 of the primary materials and colors of the nearest wall of the primary building (but excluding exposed CMU block) or a vegetative screen planted along the full length of the area to be screened and at least 8 feet high at the time of planting. Confirm compliance with this code. | Compliance to this code is confirmed. See SDP-1 showing 8' tall opaque fencing around outdoor storage area. Detail of the opaque fence is shown on detail #4 on sheet SDP-2
Planning | LANDSCAPING and IRRIGATION NOTES Please add the following notes from the IDO to the landscaping and Irrigation plan notes: (SEE COMMENT SHEET FOR FULL LIST OF NOTES) | All notes were added to both landscape plans (LS-101 and LS-102)
ABCWUA | Pay pro rata charges | GB paid. Receipt sent 7/26. See attached copy of receipt.
Parks and Rec | Match infrastructure list and site plan to read 10' concrete sidewalk | The 10’ sidewalk/path along Central is now specified as being concrete instead of asphalt.