## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A10E002A |  | Project Name: |  | Seville Subdivision
NPDES Id. No. | Not identified |  | Location: |  | Brookline Dr. NW
2021-05-28 |  | Owner |  |  |  | Contractor
Operator |  | John R. DeBassige
Contact name & title |  | John R. DeBassige
e-mail |  | jrdebassige@yahoo.com | [8 empty] | E2RC
Contact Phone # |  | 505-710-3775
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 2:45 PM-2:55 PM |  |  |  | Rain
Construction Phase: |  | earthwork/grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 88 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Sediment in the street. Sweep and remove sediment from the street daily. | [9 empty] | 2021-05-03
2 | Domestic waste on site. Remove domestic and construction waste daily and place into an approved waste container. | [9 empty] | 2021-05-31
3 | No posting of NOI permit coverage. Post signage of NOI permit coverage in a location clearly visible to the public.
4 | No erosion and sediment controls along West boundary of the site. Install silt fence or another BMP along the West boundary.
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes: | No activity during this inspection.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action