## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A10E002A |  | Project Name: |  | Brookline Subdivision | [5 empty] | jrdebassige@yahoo.com
NPDES Id. No. | NMR10040J & NMR100406 |  | Location: |  | Brookline Dr. NW | [5 empty] | 505-710-3775
2025-09-04 |  | Owner |  |  |  | Contractor
Operator |  | John R. DeBassige |  |  |  | Little Bubbas Construction, LLC
Contact name & title |  | John R. DeBassige |  |  |  | Richard Medina
e-mail |  | jrdebassige@yahoo.com |  |  |  | littlebubbasconstruction@gmail.com |  |  |  |  | E2RC
Contact Phone # |  | 505-710-3775 |  |  |  | 505-433-2220
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Inactive | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | cloudy |  | Temperature: ~ |  |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2025-08-27 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Stabilization - This site was graded several years ago and appears to have been hydro-seeded/mulched. Vegetative growth has not been established, and the hydro-seed has weathered away, exposing bare soil over the majority of the site in violation of CGP Part 2.2.14. Required mitigation: Stabilization is met if the area has been seeded or planted to establish vegetation that provides 70 percent or more of the vegetative cover native to local undisturbed areas within three years per CGP Part 2.2.14.c. | [9 empty] | 2021-05-03
2021-05-31
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | N/a | Latest report Date: |  | 2025-03-04
Notes: | Inactive site, previously graded, vertical not started yet.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action