## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A10E010 |  | Project Name: |  | SAMS Academy
NPDES Id. No. | NMR1005HZ |  | Location: |  | 6441 Ventura Rd. NW
2023-03-23 |  | Owner |  |  |  | Contractor
Operator |  | Martin Trust - Gerald and Victoria |  |  |  | RM SAMS, LLC
Contact name & title |  | Amanda Catanzaro Operations Director |  |  |  | Steve Nacamura
e-mail |  | acatanzaro@samsacademy.com |  |  |  | Steve@rachelmatthew.com
Contact Phone # |  | (505) 608-6441 |  |  |  | 505-792-4663.
COA Inspector |  | Doug Hughes | [5 empty] | 10:30AM |  |  |  | Rain
Construction Phase: |  | Landscaping | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 62 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2022-12-03 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NOI and deed received. Thank you.
2 | Permit coverage wasn't posted. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of- way per CGP 1.5.
3 | Stabilization is incomplete - You must continue permit coverage, self-inspections, SWPPP and BMP maintenance until the City determines that the Final Stabilization Criteria CGP2.2.14.c has been satisfied. Then you must remove the BMPs and send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP. This step is independent of the Certificate of Occupancy with the City. Please copy me with the documentation and the EPA’s acceptance of the NOT.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | ?
Notes:
The point of contact is Steve Hernandez at 228-1401. Amanda Catanzaro is SAMS Operations Director at (505) 608-6441.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action