## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E011I |  | Project Name: |  | McMahon Market Place Lots 9B, 9C, and 9D
NPDES Id. No. | NMR10059B |  | Location: |  | 5710 McMahon Blvd
2022-12-16 |  | Owner |  |  |  | Contractor
Operator |  | JMD-McMahon, LLC |  |  |  | Wilger
Contact name & title |  | Doug Peterson |  |  |  | john Wilger
e-mail |  | doug@petersonproperties.net
Contact Phone # |  | 884-3578
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 4:45PM |  |  |  | Rain
Construction Phase: |  | No personel or equipment present | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2022-12-05 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Coverage was not posted on the Inspections Plus sign or anywhere else. The sign was under tumble weeds and not visable from the road. The NPDES coverage needs posted and must be readable from the road.
2 | NOI expired, not accurate and not approved by the City. NMR1002NB expired on 2/16/22, a new permit was obtained NMR10059B for a reduced area, 1 ac instead of the previous 2.5 acres, and with a site/project name that is not specific. The new NOI must be corrected to accurately reflect the whole site and be approved by the City of Albuquerque.
3 | Silt fence down on about 20 % of site.
4 | Stabilization missing. The site needs to be stabilized per CGP2.2.14. Inspections and BMP maintenance must continue until all areas of land disturbance are stabelized.
5 | SWPPP and reports weren't available on site and its location wasn't on a sign. SWPPP and reports must be available on site and up-to-date.
6 | Washout along south boundary. Remove dried washout and contaminated dirt in waste container.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | 2020-08-25
Notes: | SWPPP hasn’t been checked so SWQ team and deligation unknown.
But Inspeections Plus submited new, downsized ESC Plan and NOI for review so assume they are the team.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action