## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E011J |  | Project Name: |  | McMahon 9C & D
NPDES Id. No. | NMR10069S |  | Location: |  | 5770 McMahon Blvd NW
2026-02-17 |  | Owner |  |  |  | Contractor
Operator |  | JMD - McMahon, LLC
Contact name & title |  | Doug Peterson
e-mail |  | doug@petersonproperties.net
Contact Phone # |  | 505-884-3578
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1:45pm |  |  |  | Rain
Construction Phase: |  | Inactive - preconstruction | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Windy |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Washout - Concrete washout was found in several areas of your property in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so that no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow for liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground. Remove and dispose of hardened concrete waste consistent with your handling of other construction wastes.
2 | BMPs - The perimeter silt fence is in disrepair in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The posting and the SWPPP should remain on-site once construction activity proceeds.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action