## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E017 |  | Project Name: |  | Unser/McMahonLots1 & 3-7
NPDES Id. No. | NMR1004PN |  | Location: |  | 10745 Unser Blvd
2024-09-19 |  | Owner |  |  |  | Contractor
Operator |  | Holly Partners LLC.
Contact name & title |  | Yogesh Patel
e-mail |  | yogi1020@gmail.com
Contact Phone # |  | 275-8223
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:30pm |  |  |  | Rain
Construction Phase: |  | Activity on some lots, stockpiles | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-08-31 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Stabilization - The stockpiles have not been stabilized in violation of CGP Part 2.2.14. Required mitigation: Initiate the installation of stabilization measures immediately in areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days and complete the installation of stabilization measures as soon as practicable, but no later than seven calendar days after stabilization has been initiated per CGP Part 2.2.14
2
3
4
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2024-09-10
]
Notes:
Lots 2, 3, 8, and 9 have been transferred to new owners. Tierra West prepared the SWPPP and Inspection Plus has been doing inspections. Yogesh Patel has signed a blank Delegation of Authority. The EPA does not allow Delegation of Authority to a third party. Inspections Plus plans to have the site stabilized by the end of the month.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.com

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action