## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E017 |  | Project Name: |  | Unser/McMahonLots1 & 3-7
NPDES Id. No. | NMR1004PN |  | Location: |  | 10745 Unser Blvd
2025-03-03 |  | Owner |  |  |  | Contractor
Operator |  | Holly Partners LLC.
Contact name & title |  | Yogesh Patel
e-mail |  | yogi1020@gmail.com
Contact Phone # |  | 275-8223 / 505-710-0307
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:30pm |  |  |  | Rain
Construction Phase: |  | Activity on some lots, stockpiles | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Windy |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
Please provide the most current inspection report.
Check the perimeter silt fences for wind damage.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2024-09-10
Notes:
Lots 2, 3, 8, and 9 have been transferred to new owners. Tierra West prepared the SWPPP and Inspection Plus has been doing inspections. Yogesh Patel has signed a blank Delegation of Authority. The EPA does not allow Delegation of Authority to a third party.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.com

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action