## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File # | A11E017A |  | Project Name: |  | Dunkin at Unser
NPDES ID # | NMR100783 |  | Location: |  | 10600 Unser Blvd NW
2026-02-19 |  | Owner |  |  |  | Contractor
Operator |  | NMR Properties LLC |  |  |  | Insight Construction, LLC
Contact name & title |  | Murad Fazal |  |  |  | Robert Boulier
Contact e-mail |  | muradf@fdngroup.com |  |  |  | robert@insightnm.com | [5 empty] | Snow
Contact Phone # |  | 630-878-9965 |  |  |  | 505-553-4850 | [5 empty] | Clear
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Interiors, curb and gutter, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The inspection reports were present, but they were not up-to-date in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2 | Washout - The washout container is leaking concrete wash water onto bare ground in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Yes
| Discharge off-site? |  |  | No | [6 empty] | No
| Self-Inspection Reports? |  |  | Yes | Latest report Date: |  | 2025-12-30
Notes: | The SWPPP was located in the center unit with the rest of the construction plans.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action