## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E017C |  | Project Name: |  | Tidal Wave Auto Spa
NPDES Id. No. | NMR1005J2 |  | Location: |  | 10601 Unser Blvd
2024-06-14 |  | Owner |  |  |  | Contractor
Operator |  | TWAS Properties LLC |  |  |  | Skarsgard Construction
Contact name & title |  | Ryan Crumley |  |  |  | Jason Skarsgard
e-mail |  | ryan.crumley@twavelead.com |  |  |  | jason@skarsco.com
Contact Phone # |  | 706-647-0414 |  |  |  | 505-262-2323
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | Verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-10 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP Map is not current and does not show the parking and storage area across the access road in violation of CGP Part 7.4.1. The self-inspection reports were unavailable at the time of inspection in violation of CGP Part 4.7.3. Required mitigation: You must modify your SWPPP, including the site map(s), within seven days whenever you make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPP per CGP Part 7.4.1. You must keep a copy of all inspection reports at the site or at an easily accessible location so that it can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2 | There is sediment along the access road in between the active construction site and the parking/storage area caused by track-out in violation of CGP Part 2.2.4. Required mitigation: Where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside of your site, remove the deposited sediment by the end of the same business day in which the track-out occurs. Remove the track-out by sweeping, shoveling, or vacuuming these surfaces per CGP Part 2.2.4.
3 | There was concrete washout on bare soil around the provided washout container in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground per CGP Part 2.3.4.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes: | Mr. Crumley is not reachable by phone.
Construction entrance for parking/storage area is full of sediment and needs repair/maintenance to reduce track-out. The SWPPP contact information on the posting is incorrect and should be updated. Sediment removal and inlet protection is suggested for the clogged storm drain on the southwest side of the construction site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action