## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E017C |  | Project Name: |  | Tidal Wave Auto Spa
NPDES Id. No. | NMR1005J2 |  | Location: |  | 10601 Unser Blvd
2024-09-10 |  | Owner |  |  |  | Contractor
Operator |  | TWAS Properties LLC |  |  |  | Skarsgard Construction
Contact name & title |  | Ryan Crumley |  |  |  | Jason Skarsgard
e-mail |  | ryan.crumley@twavelead.com |  |  |  | jason@skarsco.com
Contact Phone # |  | 706-647-0414 |  |  |  | 505-262-2323
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:30am |  |  |  | Rain
Construction Phase: |  | stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-08-31 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Stabilization - The area of the neighboring property has been mitigated and is inactive. The disturbed land lacks stabilization in violation of CGP Part 2.2.14. Required mitigation: Initiate the installation of stabilization measures immediately in any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days and complete the intallation of stabilization measures as soon as practicable, but no later than 14 calendar days per CGP Part 2.2.14.
2
3
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes: | Mr. Crumley is not reachable by phone.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action