## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E017C |  | Project Name: |  | Tidal Wave Care Wash
NPDES Id. No. | NMR1005J2 |  | Location: |  | 10601 Unser Blvd
2023-04-05 |  | Owner |  |  |  | Contractor
Operator |  | TWAS Properties LLC |  |  |  | Scarsgard Construction
Contact name & title |  | Ryan Crumley |  |  |  | Jason Skarsgard
e-mail |  | ryan.crumley@twavelead.com |  |  |  | jason@skarsco.com
Contact Phone # |  | 706-547-0414 |  |  |  | 262-2323
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10:30AM |  |  |  | Rain
Construction Phase: |  | Graded Lot 2 no construction active, lot is disturbed | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-03-16 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None - all previous areas of concern have been mitigated
2
3
4
5
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | n/a | Latest report Date: |  | 2023-03-22
Notes:
emailed ESC Plan approval leter and noed all previous AOC Mitigated
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action