## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E017C |  | Project Name: |  | Tidal Wave Care Wash
NPDES Id. No. | NMR1005J2 |  | Location: |  | 10601 Unser Blvd
2023-05-08 |  | Owner |  |  |  | Contractor
Operator |  | TWAS Properties LLC |  |  |  | Scarsgard Construction
Contact name & title |  | Ryan Crumley |  |  |  | Jason Skarsgard
e-mail |  | ryan.crumley@twavelead.com |  |  |  | jason@skarsco.com
Contact Phone # |  | 706-647-0414 |  |  |  | 262-2323
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10:30AM |  |  |  | Rain
Construction Phase: |  | Graded Lot 2 no construction active, lot is disturbed | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-03-16 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Posting sign is laying on the ground and must be replaced
2 | Silt Fence is down in the North east corner and must be reset. It is full of sediment and needs maintained in several other places.
3
4
5
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | n/a | Latest report Date: |  | 2023-05-04
Notes:
Tried to call Mr Crumley and operator said he doesn't have an extension and can only be reached by email. SWPPP isn't available onsite so not checked, and City is on distribution list for self inspection reports.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action