## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E018 |  | Project Name: |  | Take Five Oil Change
NPDES Id. No. | NMR1007LC |  | Location: |  | 10830 Unser Blvd NW
2025-12-16 |  | Owner |  |  |  | Contractor
Operator |  | Albuquerque-Unser Take Five, LLC |  |  |  | White Sands Construction, Inc.
Contact name & title |  | Glen Cherry |  |  |  | McChristie Curry
e-mail |  | glen.cherry@durbangroup.com |  |  |  | kimber@whitesandsconstruction.com |  |  |  |  | mcchristie@whitesandsconstruction.com
Contact Phone # |  | 704-319-8337 |  |  |  | 857-437-7816
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1pm |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 58 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-11-20 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The inspection reports need to be certified by the owner's signatory (Albuquerque-Unser Take Five, LLC) in violation of CGP Part 4.7.2. Required mitigation: Each inspection report must be signed by the operator's signatory in accordance with CGP Appendix G, Part G.11 per CGP Part 4.7.2. The EPA does not allow a Delegation of Authority to a third party. The delegated authority must be part of Albuquerque-Unser Take Five, LLC, not White Sands Construction.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-11-26
Notes:
The violations related to starting land disturbing activities without SWQ approval have been mitigated.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action