## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E018 |  | Project Name: |  | Take Five Oil Change
NPDES Id. No. | NMR1007LC |  | Location: |  | 10830 Unser Blvd NW
2026-02-17 |  | Owner |  |  |  | Contractor
Operator |  | Albuquerque-Unser Take Five, LLC |  |  |  | White Sands Construction, Inc.
Contact name & title |  | Glen Cherry |  |  |  | McChristie Curry
e-mail |  | glen.cherry@durbangroup.com |  |  |  | kimber@whitesandsconstruction.com |  |  |  |  | mcchristie@whitesandsconstruction.com
Contact Phone # |  | 704-319-8337 |  |  |  | 857-437-7816
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2:30pm |  |  |  | Rain
Construction Phase: |  | Verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Windy |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | SWPPP - There are several violations related to the inspection reports. There was no date of inspection on the reports in violation of CGP Part 4.7.1. The inspection reports are missing the owner's signature in violation of CGP Part 4.7.2. There is no training certificate in the SWPPP for the inspector on the reports in violation of CGP Parts 6.3 and 7.2.2. Required mitigation: Each inspection report must include the inspection date per CGP Part 4.7.1.a. Each inspection report must be signed by the operator's signatory in accordance with CGP Appendix G, Part G.11 per CGP Part 4.7.2. The EPA does not allow a Delegation of Authority to a third party. The delegated authority must be part of Albuquerque-Unser Take Five, LLC, not White Sands Construction. Include documentation in your SWPPP that members of the stormwater team responsible for conducting inspections pursuant to Part 4 (Inspections) have received the training required by CGP Part 6.3 (Training Requirements for Persons Conducting Inspections).
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | ??
Notes:
The superintendent had the SWPPP in his truck.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action