## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A11E018A |  | Project Name: |  | IHOP/Paris Baguette
NPDES Id. No. | NMR1006PM |  | Location: |  | 10850 Unser Blvd NW
2025-03-03 |  | Owner |  |  |  | Contractor
Operator |  | Uncer Property, LLC |  |  |  | Confederated Builders
Contact name & title |  | Mohamad Touffaha
e-mail |  | mtouffaha@gmail.com
Contact Phone # |  | 316-308-5507
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | scrubbed | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Windy |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-04 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The self-inspection reports were not current in violation of CGP Part 4.7.3. The stormwater team was not properly identified in violation of CGP Part 7.2.2. Required mitigation: You must keep a copy of all self-inspection reports at the site or at an easily accessible location so that they can be made immediately available during an on-stie inspection per CGP Part 4.7.3. CGP 7.2.2 Stormwater Team. “Identify the personnel (by name and position) that you have made part of the stormwater team pursuant to Part 6.1, as well as their individual responsibilities, including which members are responsible for conducting inspections. Include verification that each member of the stormwater team has received the training required by Part 6.2. Include documentation that members of the stormwater team responsible for conducting inspections pursuant to Part 4 have received the training required by Part 6.3. If personnel on your team elect to complete the EPA inspector training program pursuant to Part 6.3a, you must include copies of the certificate showing that the relevant personnel have completed the training and passed the exam. If personnel on your team elect to complete a non-EPA inspector training program pursuant to Part 6.3b, you must include documentation showing that these persons have successfully completed the program and their certification or license is still current. You must also confirm that the non-EPA inspector training program satisfies the minimum elements for such programs in Part 6.3b.” Include written documentation that the non-EPA inspector training program satisfies the minimum elements for such programs in Part 6.3b.
2 | Stabilization - Land disturbance has been inactive without stabilization for more than 14 calendar days in violation of CGP Part 2.2.14. Required mitigation - Initiate the installation of stabilization measures immediately in any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days and complete the installation of stabilization measures as soon as practicable, but no later than 14 calendar days per CGP Part 2.2.14.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2024-09-23
Notes:
SWPPP is in box on posting board.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action