## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A12E008B1 |  | Project Name: |  | Golf Course and Westside Blvd - Circle K
NPDES Id. No. | NMR10074M |  | Location: |  | 10850 Golf Course Rd NW
2025-11-19 |  | Owner |  |  |  | Contractor
Operator |  | Circle K Stores Inc. |  |  |  | Black Canyon Construction
Contact name & title |  | Mark Tate |  |  |  | Logan Green
e-mail |  | mtate@circlek.com |  |  |  | logan@bcanyon.com
Contact Phone # |  | 303-903-1116 |  |  |  | 830-331-7440
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Utilities, landscaping, interiors | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-10-14 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The SWPPP is not certified by all operators in violation of CGP Part 7.2.10. The map included in the SWPPP does not match the City-approved ESC Plan that utilizes sediment traps/ponds in violation of CGP Part 7.4.1. There are construction support activities on neighboring property and stormwater controls not marked on the SWPPP map in violation of CGP Part 7.2.4. The construction exit onto Golf Course Rd is not installed with Best Engineering Practices in violation of CGP Part 2.1.2. The self-inspection reports were not available for review during the inspection in violation of CGP Part 4.7.3. Required mitigation: Your signatory must sign and date your SWPPP in accordance with CGP Appendix G, Part G.11. You must modify your SWPPP, including the site map(s), within 7 days to reflect any revisions to applicable Federal, State, Tribal, or local requirements that affect the stormwater controls implemented at the site per CGP Part 7.4.1.e. Include a legible map, or series of maps, showing locations of on-site and off-site construction support activity areas per CGP Part 7.2.4.b.vii. Design and install all stormwater controls in accordance to good engineering practices, including applicable desgin specifications per CGP Part 2.1.2. You must keep a copy of all inspection reports at the site or at an easily accessible location so they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2 | Washout - The concrete washout container (located on neighboring property) is leaking onto bare ground in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
Concrete washout is leaking from the washout container. A poorly installed construction exit onto Golf Course Rd. A rejected ESC Plan was used during construction, not the approved ESC Plan showing temporary sediment traps as stormwater controls during the construction process. Stockpiles, parking, and a washout container located on neighboring property that are not identified in the SWPPP.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action