## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A12E008B2 |  | Project Name: |  | Golf Course Rd and Westside Blvd
NPDES Id. No. | NMR10061I |  | Location: |  | 10850 Golf Course Rd NW
2025-03-03 |  | Owner |  |  |  | Contractor
Operator |  | Dennis & George LLC |  |  |  | Desert Fox paving
Contact name & title |  | Dennis Carpenter |  |  |  | Francisco H
e-mail |  | denniscarpenter1@aol.com |  |  |  | FranciscoH@yahoo.com
Contact Phone # |  | 505-269-1812 |  |  |  | 505-553-0207
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1pm |  |  |  | Rain
Construction Phase: |  | Paving complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Windy |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | A portable toilet was found on its side in violation of CGP Part 2.3.3.f. Required mitigation: For sanitary waste, position portable toilets so they are secure and will not be tipped or knocked over and are located away from receiving waters, storm drain inlets, and constructed or natural site drainage features per CGP Part 2.3.3.f.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-09-04
Notes:
SWPPP is in 5 gallon bucket at posting sign
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action