## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A12E008B2 |  | Project Name: |  | Golf Course Rd and Westside Blvd
NPDES Id. No. | NMR10061I |  | Location: |  | 10850 Golf Course Rd NW
2024-10-21 |  | Owner |  |  |  | Contractor
Operator |  | Dennis & George LLC |  |  |  | Desert Fox paving
Contact name & title |  | Dennis Carpenter |  |  |  | Francisco H
e-mail |  | denniscarpenter1@aol.com |  |  |  | FranciscoH@yahoo.com
Contact Phone # |  | 505-269-1812 |  |  |  | 505-553-0207
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 11:40am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-10-19 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | No deficiencies, all previos areas of concern were mitigated
2
2.1 | Discharge off site? (Y/N) |  |  | yes | [6 empty] | yes
4 | Self Inspection Reports |  |  | ok | Latest report Date: |  | 2024-08-21
Notes: | The SWPPP is in a box on the back of the sweeper.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505-803-6155)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action