## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A12E008B2 |  | Project Name: |  | Golf Course Rd and Westside Blvd
NPDES Id. No. | NMR10061I |  | Location: |  | 10850 Golf Course Rd NW
2024-08-15 |  | Owner |  |  |  | Contractor
Operator |  | Dennis & George LLC |  |  |  | Desert Fox paving
Contact name & title |  | Dennis Carpenter |  |  |  | Francisco H
e-mail |  | denniscarpenter1@aol.com |  |  |  | Deserfoxpavingfranciscoh@yahoo.com
Contact Phone # |  | 505-269-1812 |  |  |  | 505-553-0207
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 11:40am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 100 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-30 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Posting 'The permit coverage posting was not located during the inspection in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, as per CGP Part 1.5.
2 | The SWPPP and self-inspection reports were not available at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: The SWPPP, including the SWPPP Map, Self Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3. The operator’s signature is required on a certification statement on the SWPPP per CGP 7.2.10 and on each inspection report per CGP 4.7.2 and Appendix ‘I’ I.11. See Construction General Permit (CGP) Frequent Questions ¦ US EPA for further guidance.
3 | Sediment - Sediment has been tracked out of the Construction Exit and has not been removed from the pavement in violation of CGP 2.2.4.d. Required mitigation: Implement additional track-out controls as necessary to ensure that sediment removal occurs prior to vehicle exit. Per CGP 2.2.4.c. Where sediment has been tracked from your site onto paved roads and sidewalks, remove the deposited sediment by the end of the same business day. Remove the track-out by sweeping, shoveling, or vacuuming these surfaces or using other similarly effective means of sediment removal. You are prohibited from hosing or sweeping tracked-out sediment downstream per CGP 2.2.4.d
2.1 | Discharge off site? (Y/N) |  |  | yes | [6 empty] | yes
4 | Self Inspection Reports |  |  | no | Latest report Date: |  | N/A
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505-803-6155)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action