## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A12E008B2 |  | Project Name: |  | Golf Course Rd and Westside Blvd
NPDES Id. No. | NMR10061I |  | Location: |  | 10850 Golf Course Rd NW
2025-05-19 |  | Owner |  |  |  | Contractor
Operator |  | Dennis & George LLC |  |  |  | Desert Fox paving
Contact name & title |  | Dennis Carpenter |  |  |  | Francisco H
e-mail |  | denniscarpenter1@aol.com |  |  |  | FranciscoH@yahoo.com
Contact Phone # |  | 505-269-1812 |  |  |  | 505-553-0207
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Paving complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Rain |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Posting - CGP coverage was not posted so it is visible from the public road nearest to the active part of the construction site, using a font large enough to be readily viewed from a public right-of-way in violation of CGP 1.5. Required Mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP 1.5.
2 | The SWPPP and self-inspection reports were not available on-site during the inspection in Violation of CGP 7.3, City Ordinance § 14-5-2-11(C)(1), and CGP 4.7.3. Required Mitigation: The SWPPP, including the SWPPP Map, Self Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
2 | Self Inspection Reports |  |  | missing | Latest report Date: |  | ?
Notes:
SWPPP was missing.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action