## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A12E008D |  | Project Name: |  | Wintergreen Apartments
NPDES Id. No. | NMR1004LL |  | Location: |  | 10800 Golf Course Rd NW
2023-09-25 |  | Owner |  |  |  | Contractor
Operator |  | Wintergreen Apartments, LLC |  |  |  | Snyder Construction
Contact name & title |  | K P Stalland |  |  |  | Ben Sepehripour
e-mail |  | peterstalland@stalland.net |  |  |  | bsepehriour@snyder-const.com
Contact Phone # |  | 651-433-0155
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:30am |  |  |  | Rain
Construction Phase: |  | vertical, partially paved | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-09-13 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Washout was observed on bare ground in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and lined pit and do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground as per CGP Part 2.3.4. Remove and dispose of hardened concrete waste consistent with handling of other construction wastes.
2 | The current NOI for the owner included with the SWPPP contains incorrect information. The operator name for the current NOI, K. Peter Stalland, needs to be changed to Wintergreen Apartments LLC to match with the owner of the property listed in Bernalillo County tax records and to match the approved but expired NOIs. This is a violation of the City Ordinance 14-5-2-11. Required mitigation: Amend or file a new NOI with the correct operator name, Wintergreen Apartments LLC. If filing a new NOI is required, terminate the incorrect NOI. Email the corrected/new NOI to the City Stomwater Team to update the files.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-09-13
Notes:
Erosion observed starting at an inundated stormwater drain inlet that is spreading past the perimeter silt fence.
In accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action