## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | A14E019 |  | Project Name: |  | Dutch Brothers 528 - Work Order & Tract 2
NPDES Id. No. | NMR1004R9 |  | Location: |  | 3615 HWY 528
2023-03-23 |  | Owner |  |  |  | Contractor
Operator |  | Western Hills Real Estate/Development
Contact name & title |  | Julian Garza
e-mail |  | rio7712@aol.com
Contact Phone # |  | 505-269-1179
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11AM |  |  |  | Rain
Construction Phase: |  | final inspection -grading and sidewalk incomplete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-03-16 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Permit coverage wasn't posted. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of- way per CGP 1.5
2 | SWPPP wasn’t available on site at time of inspection, so it couldn't be checked to see if it is up-to-date. - Provide a scanned copy of the up-to-date SWPPP with all reports to the Storm Water Quality Section at 600 2nd St NW suite 400 - Jhughes@cabq.gov - Per CGP 4.8.2
3 | Stabilization was missing - You must continue permit coverage, self-inspections, SWPPP and BMP maintenance until the City determines that the Final Stabilization Criteria CGP2.2.14.c has been satisfied. Then you must remove the BMPs and send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP. This step is independent of the Work Order. Please copy me with the documentation and the EPA’s acceptance of the NOT.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | n/a
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action