## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B10E003C3B |  | Project Name: |  | McDonald's 30-0260
NPDES Id. No. | NMR1006BQ |  | Location: |  | 9500 Universe Blvd NW
2024-07-18 |  | Owner |  |  |  | Contractor
Operator |  | McDonald's USA, LLC |  |  |  | Barnsley Construction LLC
Contact name & title |  | Alex Breeden |  |  |  | Dan Barnsley
e-mail |  | alex.breeden@us.mcd.com |  |  |  | dan@barnsleyconstruction.com
Contact Phone # |  | 630-207-0289 |  |  |  | 505-264-0251
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2:30pm |  |  |  | Rain
Construction Phase: |  | verticals, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-12-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The self-inspection reports are not being sent to the superintendent and were not available at the time of inspection in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location, so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action