## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B10E003J |  | Project Name: |  | Champion Xpress
NPDES Id. No. | NMR1004XB |  | Location: |  | 9600 Universe Blvd
2023-04-05 |  | Owner |  |  |  | Contractor
Operator |  | VIA Real Estate, LLC |  |  |  | 7B Building and Development
Contact name & title |  | Jordan Merchant |  |  |  | Jesse Torrez
e-mail |  | jordan@7bdev.com |  |  |  | jesse@7bdev.com
Contact Phone # |  | 806-368-7843 |  |  |  | 505-553-9228
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Construction is nearing completion | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-03-16 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | none - all previous violations have been mitigated
2
3
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2023-03-31
You must continue permit coverage, self-inspections, SWPPP and BMP maintenance until the City determines that the Final Stabilization Criteria CGP2.2.14.c has been satisfied. Then you must remove the BMPs and send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP. This step is independent of the Certificate of Occupancy. Please copy me with the documentation and the EPA’s acceptance of the NOT.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action