## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B10E003J |  | Project Name: |  | Champion Xpress Car Wash
NPDES Id. No. | NMR1004XB |  | Location: |  | 9640 Universal Blvd NE
2023-06-13 |  | Owner |  |  |  | Contractor
Operator |  | VIA Real Estate, LLC |  |  |  | 7B Building and Development
Contact name & title |  | Jordan Merchant |  |  |  | Jesse Torrez
e-mail |  | jordan@7bdev.com |  |  |  | jesse@7bdev.com
Contact Phone # |  | 806-368-7843 |  |  |  | 505-553-9228
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 9:30am |  |  |  | Rain
Construction Phase: |  | CO/Stabilization | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | In accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date:
Notes: | One prior violation that was mitigated as per the follow-up inspection.
2nd reminder to file NOT after final stabilization. Evidence of washout and materials/waste storage on neighboring lot. There is no construction activity on the neighboring lot(s).
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action