## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B14E010C |  | Project Name: |  | Take 5 Car Wash Coors
NPDES Id. No. | NMR1005E5 |  | Location: |  | 10084 Coors Blvd NW
2024-08-16 |  | Owner |  |  |  | Contractor
Operator |  | Boing US Holdco, Inc. |  |  |  | Spinoff Construction
Contact name & title |  | Jorge Primo Planta |  |  |  | Zane Dirkson
e-mail |  | Jorge.planta@drivenbrands.com |  |  |  | zdirksen@Spinoffconstruction.com
Contact Phone # |  | 919-699-7198 |  |  |  | 623-432-6226 |  |  |  |  | 6226
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 11AM |  |  |  |  | Rain
Construction Phase: |  | Sidewalks C&G & Subgrade | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-07-20 |  |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | All of the previous violations have been mitigated, and construction is nearly complete. The City inspected the site on 8/12/24 and noted gravel base course being imported. When we returned on 8/16/24, the disturbed portions of Lot 5 had been stabilized with Gravel, thus eliminating the prior need to show the area of construction support on Lot 5 on the SWPPP map or to provide the NOI for the owner of Lot 5. The gravel base course covered most of the dirt areas on site, so the stormwater controls (BMPs) are no longer needed. The offsite sediment had been removed. After you verify the Conditions for Terminating CGP Coverage Per CGP 8.2, please file your NOT and provide a copy to me.
2.1 | Discharge off site? (Y/N) |  |  | yes | [7 empty] | yes
4 | Self Inspection Reports |  |  | ok | Latest report Date: |  | 2024-07-30
Notes:
The SWPPP is in the Take 5 building.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action