## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B14E010D |  | Project Name: |  | 7 Bar Retail(Cottonwood Crossing II Lots 2A & 2B)
NPDES Id. No. | NMR1006P0 |  | Location: |  | 10088 and 10080 Coors Blvd SE
25/02/03 |  | Owner |  |  |  | Contractor
Operator |  | A Management Corp. | [9 empty] | mark.asplund@hakesbrothers.com
Contact name & title |  | Pierre Amestoy |  |  |  | Peter Steen
e-mail |  | pierre@Amestoy.net
Contact Phone # |  | 822-0044 |  |  |  | 975-6140
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 11:20 |  |  |  |  | Rain
Construction Phase: |  | Landscaping | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 55 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None - previous violations have been mitigated.
2
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | OK | Latest report Date: |  | 2025-01-07
Notes:
The SWPPP was in the lockbox on back of the sign
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505-803-6155)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action