## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B14E013 |  | Project Name: |  | Demi's Pavilion
NPDES Id. No. | NMR1006QB |  | Location: |  | 10210 Coors Rd NW
2026-02-12 |  | Owner |  |  |  | Contractor
Operator |  | CDR Holdings, LLC
Contact name & title |  | Charles Nguyen
e-mail |  | nguyenchx@gmail.com
Contact Phone # |  | 505-264-0510
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Grading, inactive | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 65 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports were not available during the inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and all inspection reports at the site or at an easily accessible location so that they can be made immediately available during an on-site inspection per CGP Parts 4.7.3 and 7.3.
2 | Posting - The permit coverage posting was missing in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP Part 1.5.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes: | Perimeter BMPs have been repaired.
There are multiple cars parking on the property. This could cause track-out issues if there are no measures intalled to control sediment.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action