## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B17E006 |  | Project Name: |  | Ascension Subdivision
NPDES Id. No. | NMR1002JR/NMR10030E |  | Location: |  | 8820 Horizon Blvd. | [5 empty] | brian@abrazohomes.com
2022-01-20 |  | Owner |  |  |  | Contractor SI
Operator |  | TQM, LLC and Gamma Development |  |  |  | Abrazo ck@abrazohomes.com |  |  |  |  | ck@abrazohomes.com
Contact name & title |  | Brian McCarthy |  |  |  | Seth Wood
e-mail |  | brian@abrazohomes.com |  |  |  | seth@abrazohomes.com
Contact Phone # |  | 505-796-6119 |  |  |  | Seth 917-2209 CK 350-7534
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11:00am |  |  |  | Rain
Construction Phase: |  | House Construction | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-01-01 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The SWPPP is not up-to-date. The Owner/Operator Certification isn't signed nor is any Delegation of Authority (DA). There is not any mention of TQM, LLC nor their NOI, NMR10030E in the SWPPP nor on the self-inspection reports. The reports signed by the operators are not available on-site. The SWPPP Map is not up-to-date with notes about which BMPs are installed and which lots have been stabilized. The operator and his stormwater teem need to cooperate to get up-to-date SWPPP available onsite.
2 | There was minor washout in the vicinity of the washout container not significvant eneough for escalation. Please remove and dispose of the washout and direct all washwater from concrete, stucco, and paint into a lined container.
3 | There is minor sediment in the streets, not significvant eneough for escalation. Please remove.
4 | NMR10030E was not posted. When I contacted E2RC, the name and number on the posting, they said the operator has the SWPPP. Please add correct contact info for SWPPP and its location on the posting.
Yes
| Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | ok | Latest report Date: |  | 2022-01-24
Notes: | The is SWPPP located in the Sales Office behind the tv screen in the main entry.
It appears the infrastructure is complete, HOA tracts stabilized, but Gamma still ownes the vacant lots, and Abrazo (TQM, LLC - NMR10030E) ownes the lots where house construction has started. So both operators should be signing self-inspection reports and permit coverage should be posted.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes 505- 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action