## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B18E026 |  | Project Name: |  | Glass Rite
NPDES Id. No. | NMR1005UB |  | Location: |  | 5605 Venice Blvd NE
2024-06-24 |  | Owner |  |  |  | Contractor
Operator |  | Rocky Ledge Properties LLC |  |  |  | Insight Construction
Contact name & title |  | Bill Holberg |  |  |  | Dave Brown
e-mail |  | billh@glass-rite.com |  |  |  | dave@insightnm.com
Contact Phone # |  | 505-300-2420 |  |  |  | 505-888-7927
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 100 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-10 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports were not available at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
2 | There was concrete washout surrounding the waste container on bare soil in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground, as per CGP Part 2.3.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
Rocky Ledge Properties LLC has 2 active NOIs for this site. You may terminate one of them.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action