## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B18E029 |  | Project Name: |  | The Peaks by Markana Ph 2
NPDES Id. No. | NMR1004QW |  | Location: |  | 6700 Modesto Avenue NE
2022-05-09 |  | Owner |  |  |  | Contractor
Operator |  | KLA 9, LLC. |  |  |  | Kasam Construction
Contact name & title |  | Faizel Kassam |  |  |  | Stephen Pendergraft
e-mail |  | fkassam@legacy-hospitality.com |  |  |  | Spendergraft@Legacydm.net
Contact Phone # |  | 505-489-4474 |  |  |  | 720-7188
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 3:30pm |  |  |  | Rain
Construction Phase: |  | Staging | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 86 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-03-23 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Construction commenced prior to permit coverage. NOI certified on 5/6/2022, coverage starts 5/20/2022. City conditional approval for grading only on 5/10. | [9 empty] | 2021-05-03
2 | Construction commenced without any BMPs. Google earth shows the previous owner cleared all of the vegitation off of the site several times once in 2007 and again in 2013, so the condition was inherited by the new owner. Grading in the south east corner has occured in conjunction with the neighboring development owned by KLA 9, LLC. | [9 empty] | 2021-05-31
3 | Permit coverage was not posted. | [9 empty] | 2021-06-28
4 | The up-to-date SWPPP was unavailable on-site. | [9 empty] | 2021-07-06
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | n/a
Notes:
ESC Plan submited to SWQ 5/6/22 shows existing City fence on south property line when in fact the fence is 30' to 40' southof the property line.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action