## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B18E029 |  | Project Name: |  | The Peaks by Markana Ph 2
NPDES Id. No. | NMR1004QW |  | Location: |  | 6500 Glendale Avenue NE
2023-11-15 |  | Owner |  |  |  | Contractor
Operator |  | KLA 9, LLC. |  |  |  | Kasam Construction
Contact name & title |  | Faizel Kassam |  |  |  | Stephen Pendergraft
e-mail |  | fkassam@legacy-hospitality.com |  |  |  | Spendergraft@Legacydm.net
Contact Phone # |  | 505-489-4474 |  |  |  | 720-7188
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10:30am | [6 empty] | Rain
Construction Phase: |  | Staging | [12 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 55 | [5 empty] | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-08-08 |  |  |  |  | 2021-02-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [14 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | SWPPP - The offsite areas were added to the SWPPP map, but specifications for perimeter controls and stabilization were still missing on the offsite 40’ to 50’ wide strip of land disturbing activities located north of Modesto Ave and east of Glendale Ave on the Pueblo of Sandia’s property in violation of CGP 2.2.3 and CGP 2.2.14 respectively. Self-inspections were not performed during the 497 days from 6/29/22 to 11/8/23. At least 35 inspections were missed at a rate of one inspection every two weeks, not counting any missed rain event inspections. Required Mitigation: Add controls to the SWPPP map. | [9 empty] | 2021-05-03
2 | BMPs - Perimeter controls and stabilization are still missing on the offsite 40’ to 50’ wide strip of land disturbing activities located north of Modesto Ave and east of Glendale Ave on the Pueblo of Sandia’s property in violation of CGP 2.2.3 and CGP 2.2.14 respectively. Construction Exits(CE) had been reset onsite, but they didn't extend through the ROW to the paved city street. Required Mitigation: Add the missing BMPs. | [9 empty] | 2021-05-31
3 | [10 empty] | 2021-06-28
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | 35 missed | Latest report Date: |  | 2023-11-08
Notes:
SWPPP was in the construction trailer, and an updated map and inspection report were e-mailed the next day. Self-inspections were not performed during the 497 days from 6/29/22 to 11/8/23. At least 35 inspections were missed at a rate of one inspection every two weeks, not counting the missed rain event inspections. | [10 empty] | 2022-06-29 | 2023-11-08 | 497 | 35.5
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action