## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B18E031 |  | Project Name: |  | Luxelocker
NPDES Id. No. | NMR1005MA |  | Location: |  | 5601 San Diego Ave NE
2024-06-24 |  | Owner |  |  |  | Contractor
Operator |  | Albuquerque Storage Partners, LLC
Contact name & title |  | Brian Francis
e-mail |  | brian.francis@luxelocker.com
Contact Phone # |  | 928-412-1401
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2:30pm |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 100 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-10 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP is missing the operators' signatories in violation of CGP Part 7.2.10. Self-inspection reports were unavailable at the time of inspection in violation of CGP Part 4.7.3. There were no NOIs included in the SWPPP in violation of CGP Part 7.2.11. Required mitigation: Your signatory must sign and date your SWPPP in accordance with CGP Appendix G, Part G.11 per CGP Part 7.2.10. You must keep a copy of all inspection reports at the site or at an easily accessible location, so that it can be made immediately available at the time of inspection per CGP Part 4.7.3. You must include a copy of your NOI submitted to the EPA along with any correspondence exchanged between you and EPA related to coverage under the CGP per CGP Part 7.2.11.
2 | There were two areas observed to have concrete washout in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation. Do no allow liquid wastes to be disposed of through infiltration or on the ground, as per CGP Part 2.3.4.
3 | BMPs - Inlet protection measures are in need of maintenance in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | N/A
Notes:
The Delegation of Authority in the SWPPP was also blank.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action