## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Estates at Glendale Ph 3
Location: |  | 8000 Glendale NE
Site Contact Name & Agency |  | Randy Schmille |  |  |  | ESC File No. | B19E027
[6 empty] | NPDES Id. No. | NMR1001AX
Inspection Date: |  | 2019-05-10 | Start/End Time: |  | 10:05 |  | 10:25
CoA Stormwater Inspector: |  |  | Curtis Cherne | [8 empty] | Rain
Construction Phase: |  | Constructing homes | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular | X | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | rain |  |  | 45 degrees |  |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2019-04-22 |  |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Construction and domestic waste not in an acceptable container in various locations through-out site
2 | Domestic waste at subdivision outfall
3 | No sediment BMP on lot with dirt ramp
4 | Too much dirt in the street including the dirt ramp
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | request |  | Latest report Date: |  | 2019-03-01
Notes:
Will need to replace inlet protection soon - recommend cocoa mat or mulch sock
Subcontractor driving on lots to the east - blue truck
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Curtis Cherne PE 505-924-3420
|  | ccherne@cabq.gov |  |  |  |  | 2019-05-10

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action