## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B20E066 |  | Project Name: |  | 8400 & 8420 Glendale Ave NE
NPDES Id. No. |  |  | Location: |  | 8400 & 8420 Glendale Ave NE
2020-10-09 |  | Property Owner |  |  |  | Contractor
Operator |  | Las Ventanas NM, Inc
Contact name & title |  | Scott Ashcraft
e-mail |  | tscott@lasventanasnm.com
Contact Phone # |  | 505-362-6824
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 8:30-9:30am |  |  |  | Rain
Construction Phase: |  | Earthwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 69 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [11 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | These two lots have been graded and about 3700 cy fill has been stockpiled. This requires an Approved Grading and Drainage Plan and a Grading permit from Hydrology.
2 | The disturbed area is more than 1 acre so NPDES permit coverage is required and both the NOI and the ESC Plan must be approved by the City. BMPs are required.
3 | Fill has been placed in the floodplain without a Floodplain Development Permit and must be removed and the disturbed area stabelized immediately.
Items 1, 2, & 3 have not changed since the precvious inspection o9/24/20 and remained unchanged still on 10/13/20.
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | n/a
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action