## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | B20E066 |  | Project Name: |  | 8400 & 8420 Glendale Ave NE
NPDES Id. No. |  |  | Location: |  | 8400 & 8420 Glendale Ave NE
2020-11-05 |  | Property Owner |  |  |  | Contractor
Operator |  | Las Ventanas NM, Inc
Contact name & title |  | Scott Ashcraft
e-mail |  | tscott@lasventanasnm.com
Contact Phone # |  | 505-362-6824
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10am |  |  |  | Rain
Construction Phase: |  | Earthwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 69 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [11 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The stock piles were graded smooth ready for seed, silt fence in place and fill removed from floodplain.
2 | The disturbed area is more than 1 acre so NPDES permit coverage is required and both the NOI and the ESC Plan still have not been submited to the City
Yes
2.1 | Discharge off site? (Y/N) | [9 empty] | No
4 | Self Inspection Reports |  |  | requested. | Latest report Date: |  | n/a
Notes:
Violation Letter sent to owner with $500 fine.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action