## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E011B |  | Project Name: |  | Bedrock at The Trails
NPDES Id. No. | NMR1005SI |  | Location: |  | 9300 Woodmont Ave. NW
2025-03-10 |  | Owner |  |  |  | Contractor
Operator |  | Bedrock ABQ Investors, LLC (La Terra Development, LLC.) |  |  |  | LT Building Corp.
Contact name & title |  | Julia Golden |  |  |  | William Leahy President
e-mail |  | juliag@laterradev.com |  |  |  | williaml@ltbuildingcorp.com
Contact Phone # |  | 505-310-9545 |  |  |  | 310-552-0065
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1pm |  |  |  | Rain
Construction Phase: |  | verticals and grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-11-07 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | None
2 | [10 empty] | 2021-05-03
3
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | OK | Latest report Date: |  | 2025-03-05
Notes:
SWPPP will be at construction trailer, and reports will be available by QR code. The delegation of Authority from William Leahy of LT Building Corp. to Brian Anderson of Price Land Development Group is invalid because Price Land Development Group is a third party. The role of Price Land Development Group LLC is unclear. They may qualify as an Operator per CGP 1.1, but none of the Operators may delegate authority to this or any other third party per Appendix G11.2 of the CGP. All operators must sign all reports.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action