## 04.2019Form
|  | City of Albuquerque ---Stormwater Construction Site Inspection Report--- | [8 empty] | Weather: | Discharge: | Reports: | ROW:
General Information | [11 empty] | Shadow | Yes
ESC File # | C09E011B |  | Project Name: |  |  | Bedrock at The Trails (The Charlie) | [5 empty] | Yes | No
City Plan # | None |  | Location: |  |  | 9300 Woodmont Ave NW
NPDES ID # | NMR1005SI | [10 empty] | No | Requested | Sidewalk
2026-03-03 |  | Owner |  |  |  |  | Contractor |  |  |  | Snow |  | Out-of-date | Street
Operator |  | Bedrock ABQ Investors, LLC (La Terra Development, LLC) |  |  |  |  | LT Building Corp. |  |  |  | Clear |  | Unsigned | Storm Drain Inlet
Contact name & title |  | Julia Golden |  |  |  |  | William Leahy |  |  |  | Rain |  |  | Drainage Ditch
Contact e-mail |  | juliag@laterradev.com |  |  |  |  | williaml@ltbuildingcorp.com |  |  |  | Clear/Windy |  |  | Arroyo
Contact Phone # |  | 505-310-9545 |  |  |  |  | 310-552-0065 |  |  |  | Windy |  |  | Private Property
COA Inspector |  | Chancellor English |  |  |  |  | Start/End Time: |  | 11:30am |  | Cloudy |  |  | N/A
Construction Phase: |  | All phases are ongoing (Grading, foundations, verticals, interiors, paving) | [8 empty] | Sleet
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | Follow Up
Weather at time of inspection: |  |  |  | Clear/Windy |  | Temperature: ~ |  | 70
Estimated date of last storm 0.25" or greater: |  |  |  |  | 2026-01-08
Item Number | Deficiency/ Corrective Action
1 | The inspection reports were not current, and the latest one was not signed by the operators' signatories in violation of CGP Parts 4.7.2 and 4.7.3. Required mitigation: Each inspection report must be signed by the operator's signatory in accordance with CGP Appendix G, Part G.11 per CGP Part 4.7.2. You must keep a copy of all inspection reports at the site or at an easily accessible location so they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
Discharge off-site? |  | No | Right-of-way: |  |  | N/A
Self-Inspection Reports? |  | Out-of-date | Latest report Date: |  |  | 2025-12-24
Notes:
The SWPPP and reports were in the construction office at the southern corner of the property on Woodmont Ave NW.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action