## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E012A |  | Project Name: |  | Hake Brothers at Durango Units 3 and 4 | [6 empty] | Bethany Jesseph
NPDES Id. No. | NMR1003L6 |  | Location: |  | Woodmont Ave. and Sunlight Peak | [6 empty] | bethany.jesseph@hakesbrothers.com
2022-04-25 |  | Owner |  |  |  | Contractor
Operator |  | Hakes Brothers | [9 empty] | mark.asplund@hakesbrothers.com
Contact name & title |  | Chris Hakes |  |  |  | Mark Asplund
e-mail |  | chris@hakesbrothers.com |  |  |  | mark.asplund@hakesbrothers.com
Contact Phone # |  | 505-842-1700
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 2:30 - 3:00 pm |  |  |  |  | Rain
Construction Phase: |  | Vertical | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 63 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2022-03-23 |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NPDES coverage not posted for safe public viewing. Post coverage. No change since last inspection.
2 | Up-to-date SWPPP not available on-site. No change since last inspection.
3 | Concrete and stucco washout on the ground SE corner of site. Pickup washout and dispose with waste. Provide lined containers for all future washout. No change since last inspection.
4
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
2.2 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes:
Mark Aspland responded to 4/11/22 violation note by paying the fine on 4/12/22 and said in an e-mail on 4/20/22 that all violations had been mitigated. On 4/25/22 I called while at the site and left a message on his voice mail, then about 20 minutes later got a call from someone at Superior Storm water saying that they would get the site posted, washout containers reset, and SWPPP update delivered later this week but could not get any of it done that day. He said they reset the wasout container for the neighboring builder, Abrazo, last week.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action