## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E012A |  | Project Name: |  | Hake Brothers at Durango Units 3 and 4 | [6 empty] | Bethany Jesseph
NPDES Id. No. | NMR1003L6 |  | Location: |  | Woodmont Ave. and Sunlight Peak | [6 empty] | bethany.jesseph@hakesbrothers.com
2022-05-02 |  | Owner |  |  |  | Contractor
Operator |  | Hakes Brothers | [9 empty] | mark.asplund@hakesbrothers.com
Contact name & title |  | Chris Hakes |  |  |  | Mark Asplund
e-mail |  | chris@hakesbrothers.com |  |  |  | mark.asplund@hakesbrothers.com
Contact Phone # |  | 505-842-1700 |  |  |  | 252-1105
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 4pm |  |  |  |  | Rain
Construction Phase: |  | Vertical | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 77 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2022-03-23 |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
2 | SWPPP Up-to-date with 2017 NOI & CGP owner Cert and deligation of authority to Mark Aspland, available at sales off from now on. Inspector certification missing.
3
4
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
2.2 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2022-04-26
Notes:
Mark Aspland is DA 252-1105 call for SWPPP if not available at sales office. Since the SWPPP was just missing at the last inspection and not necessarily out of date, its up-to-date now, the fine will be reduced from 14 days to just the one day when it wasn't available when requested.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action