## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E013 |  | Project Name: |  | Catalonia at The Trails
NPDES Id. No. | NMR1002ET |  | Location: |  | Woodmont Ave. and Paseo Del Norte
2022-06-27 |  | Owner |  |  |  | Contractor
Operator |  | PV Catalonia, LLC
Contact name & title |  | Kevin Wechter
e-mail |  | kwechter@pacventures.com
Contact Phone # |  | 858-625-0100
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Home Construction & Final Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 94 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-06-27 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | none | [9 empty] | 2021-05-03
Yes
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2022-06-09
Notes:
All buildable lots have been transferred to DR Horton. Seed and Hydromulch were being applied which satisfys the stabilization criteria of CGP 2.2.14.a but not the Final Stabilization Criteria of CGP 2.2.14.c. The inspection frequincy may be reduced to once per month after all areas under control of PV, Catalonia, LLC have been mulched. The Pond south of the site belongs to the Community Association and is being stabilized with this project.
The SWPPP is on the back of the Posting on Woodmont across from the south pond.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action