## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E013 |  | Project Name: |  | Catalonia at The Trails
NPDES Id. No. | NMR1002ET |  | Location: |  | Woodmont Ave. and Paseo Del Norte
2023-07-12 |  | Owner |  |  |  | Contractor
Operator |  | PV Catalonia, LLC
Contact name & title |  | Kevin Wechter
e-mail |  | kwechter@pacventures.com
Contact Phone # |  | 858-625-0100
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Home Construction & Final Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Rain |  | Temperature: ~ |  |  | 98 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-03-17 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Owner Terminated coverage 9/7/2022 and made reasonably successful attempt to stabilize HOA Tracts. However silt fence (SF) was left behind on west side. Please remove SF. | [9 empty] | 2021-05-03
Yes
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | N/A
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action