## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E015 |  | Project Name: |  | The Preserve at Woodmont
NPDES Id. No. | NMR1004NN NMR1004O0 |  | Location: |  | Woodmont Ave. and Paseo Del Norte
2023-07-12 |  | Owner |  |  |  | Contractor
Operator |  | PV Trails Apartments, LLC |  |  |  | Pavilion Construction, LLC
Contact name & title |  | Kevin Wechter |  |  |  | Michael McDonald
e-mail |  | kwechter@pacventures.com |  |  |  | mmcdonald@pavillionconstruction.com
Contact Phone # |  | 858-625-0100 |  |  |  | 505-219-5408
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11:15 |  |  |  | Rain
Construction Phase: |  | The Pond is graded but no crews or equipment are onsite | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 98 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-03-17 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The SWPPP wasn't available on-site in Violation of CGP 7.3 There was nobody working onsite and the Posting said to call Michael McDonald at 505-219-5408. Michael said he hasn't had a SWPPP in over a year and that Pavilion terminated their coverage, however Pavilion's coverage under NMR1004O0 is still "active" according to the EPA. Required Mitigation: The SWPPP including Self Inspection Reports and Corrective Action Reports must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. | [9 empty] | 2021-05-03
2 | The BMPs need maintenance and maybe a reset. The Silt Fence is down in the south west corner of the site. in violation of CGP 2.1.4. Required Mitigation: Ensure that all stormwater controls (BMPs) are maintained and remain in effective operating condition during permit coverage per CGP 2.1.4. If at any time you find that a stormwater control needs routine Maintenance, you must immediately initiate the needed maintenance work and complete such work by the close of the next business day. When the problem requires a new or replacement control or significant repair, install the new or modified control and make it operational, or complete the repair, by no later than seven (7) calendar days from the time of discovery per CGP 5.2.1.
3 | There is still no evidence of Stabilization in areas where construction activities have been inactive for 14 days or more.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2023-07-11
Notes: | EPA shows both NOIs active. E2RC emailed the latest self-inspection report on 7/19/23
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action