## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E015 |  | Project Name: |  | The Preserve at Woodmont
NPDES Id. No. | NMR1004NN NMR1004O0 |  | Location: |  | Woodmont Ave. and Paseo Del Norte
2022-06-16 |  | Owner |  |  |  | Contractor
Operator |  | PV Trails Appartments, LLC |  |  |  | Pavilion Construction, LLC
Contact name & title |  | Kevin Wechter |  |  |  | Michael McDonald
e-mail |  | kwechter@pacventures.com |  |  |  | mmcdonald@pavillionconstruction.com
Contact Phone # |  | 858-625-0100 |  |  |  | 505-219-5408
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 8am-5pm |  |  |  | Rain
Construction Phase: |  | Home Construction & Final Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 94 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-03-23 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The SWPPP wasn't available on-site. There was nobody working onsite and the Posting said to call E2RC for the SWPPP 867-4040. E2RC said they gave SWPPP to Pavillion construction. | [9 empty] | 2021-05-03
2 | The siltfence east of Woodmont is falling down and needs reset preferably at the top of slope, and all of the rest of the Silt Fence is missing.
3
4
5
6 | [10 empty] | Yes
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | none
Notes:
In response to Violation Notice #1 (5/2/22) Scott Stephen's e-mail on 5/10 said trades were busy and would have mitigation complete by 5/20. At City followup inspection on 6/2 Posting and permit coverage were mitigated, but no progress on BMPs or SWPPP. Violation Notice #2 sent 6/9/22 was for no progress on BMPs and SWPPP availability onsite. Still no progress onsite on 6/16/22.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action