## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E017 |  | Project Name: |  | Dollar General
NPDES Id. No. | NMR1005RE |  | Location: |  | Universe Blvd and Rainbow Blvd NW
2024-06-20 |  | Owner |  |  |  | Contractor
Operator |  | 12 Oaks Albuquerque Universe Blvd 2020, LLC |  |  |  | B. Enterprises, LLC
Contact name & title |  | Drew Crosby |  |  |  | Billy Baca
e-mail |  | drew@12oaksdevelopment.com |  |  |  | billy.baca55@icloud.com
Contact Phone # |  | 615-896-3000 |  |  |  | 505-975-2156
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:30pm |  |  |  | Rain
Construction Phase: |  | foundations | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-10 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports were unavailable at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and all inspection reports at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
No construction office on-site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action