## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E017 |  | Project Name: |  | Dollar General
NPDES Id. No. | NMR1005RE |  | Location: |  | Universe Blvd and Rainbow Blvd NW
2024-12-26 |  | Owner |  |  |  | Contractor
Operator |  | 12 Oaks Albuquerque Universe Blvd 2020, LLC |  |  |  | B. Enterprises, LLC
Contact name & title |  | Drew Crosby |  |  |  | Billy Baca
e-mail |  | drew@12oaksdevelopment.com |  |  |  | billy.baca55@icloud.com
Contact Phone # |  | 615-896-3000 |  |  |  | 505-975-2156
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:30pm |  |  |  | Rain
Construction Phase: |  | foundations | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Stockpiles around the construction site are so close to the perimeter silt fence that the fence is either overloaded or collapsed in violation of CGP Parts 2.1.4 and 2.2.3. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4. After installation, to ensure that perimeter controls continue to work effectively, remove sediment before it has accumulated to one-half of the above-ground height of any perimeter control per CGP Part 2.2.3.c.i.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
No personnel on-site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action