## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E017 |  | Project Name: |  | Dollar General
NPDES Id. No. | NMR1005RE |  | Location: |  | Universe Blvd and Rainbow Blvd NW
2025-10-22 |  | Owner |  |  |  | Contractor
Operator |  | 12 Oaks Albuquerque Universe Blvd 2020, LLC |  |  |  | B. Enterprises, LLC
Contact name & title |  | Drew Crosby |  |  |  | Billy Baca
e-mail |  | drew@12oaksdevelopment.com |  |  |  | billy.baca55@icloud.com
Contact Phone # |  | 615-896-3000 |  |  |  | 505-975-2156
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:45am |  |  |  | Rain
Construction Phase: |  | graded, structure in place | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 65 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-10-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP is not certified by either operator in violation of CGP Part 7.2.10. There were no inspection reports available for the inspection in violation of CGP Part 4.7.3. Required mitigation: Your signatory must sign and date your SWPPP in accordance with CGP Appendix F, Part G.11 per CGP Part 7.2.10. You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
No personnel on-site. SWPPP was near the door on the sidewalk.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action