## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | C09E017 |  | Project Name: |  | Dollar General
NPDES Id. No. | NMR1005RE |  | Location: |  | Universe Blvd and Rainbow Blvd NW
2026-01-22 |  | Owner |  |  |  | Contractor
Operator |  | 12 Oaks Albuquerque Universe Blvd 2020, LLC |  |  |  | B. Enterprises, LLC
Contact name & title |  | Drew Crosby |  |  |  | Billy Baca
e-mail |  | drew@12oaksdevelopment.com |  |  |  | billy.baca55@icloud.com
Contact Phone # |  | 615-896-3000 |  |  |  | 505-975-2156
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | graded, structure in place | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Washout - Concrete has been washed out onto bare soil in violation of CGP Part 2.3.4. Required mitigation: Direct wash water to a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
No personnel on-site. SWPPP was in the foyer of the structure, but was inaccessible due to a missing key.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action