## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [12 empty] | Wexford Construction
ESC File No. | C10E001A |  | Project Name: |  | Sonata Green | [7 empty] | JL Murtagh
NPDES Id. No. | NMR1005FW |  | Location: |  | Tree Line Ave. and Universe Blvd. | [5 empty] | Sonata Green Owner, LLC; John Murtagh |  | 505-259-3397
2024-07-18 |  | Owner |  |  |  | Contractor |  |  |  |  | 702-376-5287 |  | JL@wcinm.com
Operator |  | Sonata Green, LLC. |  |  |  | Wexford Construction
Contact name & title |  | John Murtagh |  |  |  | JL Murtagh |  |  |  |  | Tim Slatunas
e-mail |  | jmurtagh@wcinm.com |  |  |  | JL@wcinm.com
Contact Phone # |  | 702-376-5287 |  |  |  | 505-259-3397 |  |  |  |  | Mike Webb | mike@enviroworksforyou.com | 505-331-6101
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 3pm |  |  |  |  | Rain
Construction Phase: |  | verticals | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 95 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-06-30 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The posting is not viewable by the general public and has been damaged in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site per CGP Part 1.5. | [9 empty] | 2021-05-03
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2014-07-02
Notes:
The SWPPP was in the construction office in one of the apartments near the leasing office.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action